## Lessons log
ID | Date | Stage / area | Type | What happened | What we would do differently | Recommendation for future projects | Logged by | Priority
L1 | 09/07/2026 | Discovery | Went badly | Supplier onboarding took three weeks against one planned - security review was not booked in advance. | Book the security review the day the contract is signed. | Add supplier security review to the standard stage-1 checklist. | A. Example | Medium

## How to use
PRINCE2-style Lessons Log - how to use
Log lessons as they happen, not at the end - by close-down everyone has forgotten the detail and moved on.
Capture positives as well as failures: a thing that went unexpectedly well is a lesson worth repeating.
A lesson is only learned when it changes something: every entry should end in a recommendation someone can act on next time.
Review the log at every stage boundary and feed relevant lessons into the next stage plan.
Guddle scaffolds a lessons-learned task into every project's final stage automatically, and keeps the log beside the rest of the project record - guddle.net.
A free PRINCE2-style template from Guddle - guddle.net. PRINCE2(R) is a registered trade mark of the PeopleCert group of companies. Guddle is an independent product, not affiliated with or endorsed by PeopleCert.