## Risk register
ID | Date raised | Raised by | Risk (cause > event > effect) | Probability (1-5) | Impact (1-5) | Score | Severity | Proximity | Response type | Response actions | Owner | Status | Last reviewed
R1 | 09/07/2026 | A. Example | Because the legacy stock system has no API (cause), the data migration may fail validation (event), delaying go-live past the peak trading window (effect). | 4 | 4 | 16 | High | This stage | Reduce | Prototype the extract early; agree a manual fallback with the supplier by end of stage 2. | T. Owner | Open | 09/07/2026

## How to use
PRINCE2-style Risk Register - how to use
Describe each risk as cause > event > effect: because of X (a fact), Y might happen (uncertain), leading to Z (the impact on objectives). Vague risks get vague responses.
Score probability and impact on a 1-5 scale (1 = very low, 5 = very high). The Score column multiplies them (1-25) and the Severity column bands the result: 15-25 High, 8-14 Medium, 1-7 Low. High risks should be treated as exceptions and escalated.
Using your organisation's own matrix? Map each axis onto 1-5 (a 3-point scale maps to 1 / 3 / 5) and keep your own descriptors in the risk description.
Response types: Avoid (remove the cause), Reduce (lower probability or impact), Transfer (e.g. insure or contract out), Accept (tolerate and monitor), Share (with a partner), Contingency (a plan that triggers if it happens).
Every open risk needs a named owner and a review date. A register nobody reviews is a list of regrets in waiting.
Prefer this maintained for you? Guddle builds the register from your project brief, keeps scores current, and its overnight analyst flags risks nobody has raised - guddle.net.
A free PRINCE2-style template from Guddle - guddle.net. PRINCE2(R) is a registered trade mark of the PeopleCert group of companies. Guddle is an independent product, not affiliated with or endorsed by PeopleCert.